## Sheet1
WS 0 - ACTIVITY 1 - PLANNER (GANT SHEET)
Workstream | Activity | 2015-01-01 | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01 | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01
WS0-Management and Coordination of the Project |  | 2015-01-01: Maria, Teo and Cath
| National coordination meetings | 2015-01-01: All; 2015-04-01: All; 2015-07-01: All; 2015-10-01: All; 2016-01-01: All; 2016-04-01: All; 2016-07-01: All; 2016-10-01: All
| Inter-country meeting | 2015-02-01: Cluj; 2016-01-01: Barca
| National activity reports | 2016-01-01: All; 2016-11-01: All; 2016-12-01: All
| National & European dissemination events | 2016-11-01: All; 2016-12-01: Ireland
WS1-Building Capacity |  | 2015-01-01: Andy-coordinating internationally
| With Roma YP- Reflect on and share what works in existing practices | 2015-01-01: All
| Inter-country training development meeting | 2015-02-01: Discuss in Cluj
| Draft training manual | 2015-01-01: Andy-coordinating internationally
Train 10 trainers | Deliver training to Bu, Ro, Li, Cy, Es | 2015-04-01: To -Bu, Ro, Li, Cy, Es - By CL, AB & BPS
| Deliver training locally | 2015-05-01: All; 2015-08-01: To train at least 15 adults/young roma facilitators
| Finalise training manual (based on WS2 evaluation) | 2016-01-01: Andy
| Further capacity building (directed by Roma YP groups in WS4) | 2016-04-01: All; 2016-10-01: All
WS2-Reflective action and inquiry to support shared evaluation |  | 2015-01-01: Abel coordinating internationally
| Develop evaluation framework & tools | 2015-01-01: Abel
| Inter-country evaluation framework meeting | 2015-02-01: Discuss in Cluj
| Evaluate WS1 training | 2015-05-01: All
| Young Roma conduct/ evaluate pilot participation projects | 2015-09-01: All- at least 30 young roma involved each country meeting 6 times
| National evaluation reports, revise evaluation framework/tools, draft papers on participation/ advocacy | 2015-11-01: All; 2015-12-01: All; 2016-01-01: All
Embed evaluation in WS4 action projects | bar: 2016-02-01 to 2016-09-01
| Final evaluation report informing WS4 participation/advocacy guides | 2016-12-01: All (Abel internationally)
WS3-Sharing information |  | 2015-01-01: Livia
| Prepare plans for website | 2015-02-01: Discuss in Cluj
| Searching for publications and linking to existing Roma projects | 2015-01-01: All
| Inter-country website development meeting | 2015-02-01: Discuss in Cluj
| Website Ready | 2015-03-01: Livia
| Set up country webpages with Young Roma | 2015-04-01: All
| Monthly website updates and quarterly web conferences by Young Roma | 2015-07-01: All
| 2/16 Disseminate training manual through web, social media & other networks | 2016-02-01: All
| Support Young Roma Lobbying | 2016-02-01: All
| Disseminate advocacy/ participation guides for young Roma and their workers | 2016-12-01: All
WS4-Embedded action, learning and change |  | 2016-01-01: Barry Coordinating nationally and internationally
| Establish and support 3 Roma children’s projects in each country | 2016-01-01: All- at least 30 YR to meet 12 times through this nine month period
| Use evaluation to review and revise strategies, recruiting new or maintain groups/participants | 2016-05-01: all
| Review, revise, recruit and maintain as above | 2016-08-01: all
| With Roma children compile multimedia data on barriers/ successes in participatory action for change | 2016-10-01: All; 2016-11-01: All; 2016-12-01: All
| Combine data creating multi-media advocacy/ participation guides for young Roma/their workers | 2016-10-01: All; 2016-11-01: All; 2016-12-01: All